## Sheet1
| EXPECTED: | ACTUAL:
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
WEBSITE IMPLEMENTATION
Homepage (expected) | bar: ACTUAL: Week 8 to ACTUAL: Week 15
Homepage (actual) | bar: ACTUAL: Week 6 to ACTUAL: Week 15
Shop Page (expected) | bar: ACTUAL: Week 8 to ACTUAL: Week 15
Shop Page (actual) | bar: ACTUAL: Week 7 to ACTUAL: Week 15
Rewards Program Page (expected) | bar: ACTUAL: Week 8 to ACTUAL: Week 15
Rewards Program Page (actual) | bar: ACTUAL: Week 8 to ACTUAL: Week 15
About Us Page (expected) | bar: ACTUAL: Week 8 to ACTUAL: Week 15
About Us Page (actual)
Contact Page (expected)
Contact Page (actual)
My Cart (expected)
My Cart (actual) | bar: ACTUAL: Week 8 to ACTUAL: Week 15
Checkout Page (expected) | bar: ACTUAL: Week 8 to ACTUAL: Week 15
Checkout Page (actual) | bar: ACTUAL: Week 8 to ACTUAL: Week 15
User Registration Page (expected) | bar: ACTUAL: Week 8 to ACTUAL: Week 15
User Registration Page (actual)
User Account Page (expected)
User Account Page (actual) | bar: ACTUAL: Week 8 to ACTUAL: Week 15
TESTING
Homepage (expected)
Homepage (actual) | bar: ACTUAL: Week 11 to ACTUAL: Week 15
Shop Page( expected)
Shop Page (actual) | bar: ACTUAL: Week 10 to ACTUAL: Week 15
Rewards Program Page (expected)
Rewards Program Page (actual) | bar: ACTUAL: Week 11 to ACTUAL: Week 15
About Us Page (expected)
About Us Page (actual)
Contact Page (expected)
Contact Page (actual) | bar: ACTUAL: Week 10 to ACTUAL: Week 15
My Cart (expected)
My Cart (actual) | bar: ACTUAL: Week 10 to ACTUAL: Week 15
Checkout Page (expected)
Checkout Page (actual) | bar: ACTUAL: Week 11 to ACTUAL: Week 15
User Registration Page (expected)
User Registration Page (actual)
User Account Page (expected)
User Account Page (actual) | bar: ACTUAL: Week 11 to ACTUAL: Week 15
DELIVERABLES
Use Cases (expected) | bar: ACTUAL: Week 8 to ACTUAL: Week 10
Use Cases (actual) | bar: ACTUAL: Week 12 to ACTUAL: Week 13
Requirements (expected) | bar: ACTUAL: Week 8 to ACTUAL: Week 10
Requirements (actual) | bar: ACTUAL: Week 12 to ACTUAL: Week 14
website prototype 2 (launched version : expected) | bar: ACTUAL: Week 8 to ACTUAL: Week 10
website prototype 2 (launched version): actual) | bar: ACTUAL: Week 12 to ACTUAL: Week 15
website prototype 1 (expected) | bar: ACTUAL: Week 6 to ACTUAL: Week 10
website prototype 1 (actual) | bar: ACTUAL: Week 11 to ACTUAL: Week 15
SPMP (expected) | bar: ACTUAL: Week 6 to ACTUAL: Week 10
SPMP (actual) | bar: ACTUAL: Week 9 to ACTUAL: Week 13