## Sheet1
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15
WEBSITE IMPLEMENTATION
Homepage | bar: Week 8 to Week 10
Shop Page | bar: Week 8 to Week 10
Rewards Program Page | bar: Week 8 to Week 10
About Us Page | bar: Week 9 to Week 10
Contact Page | bar: Week 9 to Week 10
My Cart | bar: Week 8 to Week 10
Checkout Page | bar: Week 8 to Week 10
User Registration Page | bar: Week 8 to Week 10
User Account Page | bar: Week 8 to Week 10
TESTING
Homepage
Shop Page
Rewards Program Page
About Us Page
Contact Page
My Cart
Checkout Page
User Registration Page
User Account Page
DELIVERABLES
Use Cases | bar: Week 8 to Week 10
Requirements | bar: Week 8 to Week 10
website prototype 2 (launched version)
website prototype 1 | bar: Week 6 to Week 10
SPMP | bar: Week 6 to Week 10